## Task
Table | Owner | Features | DeadLine(Max 27-4) | Status (pending,Done,CR)
Application Core
GeneralSettings | Mohmed ,Kareem | Update Data | 2026-04-25
Routes | Mohmed ,Kareem | CRUD Operations | 2026-04-25
Stations | Mohmed ,Kareem | CRUD Operations | 2026-04-25
Trains | Mohmed ,Kareem | CRUD Operations | 2026-04-25
Carriages | Ayman | CRUD Operations | 2026-04-25
CarriageClasses | Ayman | CRUD Operations | 2026-04-25
CarriagesSeats | Ayman | CRUD Operations | 2026-04-25
TripSchedules | Abdullah,Fahmi | CRUD Operations | 2026-04-25
TripDirections | Abdullah,Fahmi | CRUD Operations | 2026-04-25
Payment Operation
Booking | Ayman | Insert,Update
PaymentMethods | Ayman | Insert,Update
Transactions | Ayman | Insert
TransactionEntries | Ayman | Insert
Identity Section
AspNetUsers | Ayman | CRUD Operations | 2026-04-25
AspNetRoles | Ayman | CRUD Operations | 2026-04-25
AspNetUserRoles | Ayman | CRUD Operations | 2026-04-25
ApplicationUserOTPs | Ayman | Insert,Update | 2026-04-25
Operation Test | All Team Member | Fix Bugs and improvements

## CR
ID | Change Description | Requester | Tbl Name | Old status | New Tbl Schema | Decision | Comment | Image(google Drive link)